## Sheet1
Bug ID | Module | Screen/Page | Issue Title | Description | Severity | Expected Result | Actual Result | Status
BUG-001 | Leads | Lead Details View | Duplicate "Log First Call" Button | The "Log First Call" button is displayed twice on the Lead Details page—once in the top action bar and again inside the SLA notification card. This creates confusion regarding the primary action and results in UI redundancy. | Medium | The button should appear only once in the most appropriate location. | Two identical "Log First Call" buttons are visible on the same screen. | Open
BUG-002 | Leads | Lead Details View | Excessive White Space | Large unused spaces are present between sections and around content, reducing information visibility and requiring unnecessary scrolling. | Low | Screen space should be utilized efficiently with balanced spacing. | Significant empty space is visible across the page. | Open
BUG-003 | Leads | Lead Details View | Lead Status Displayed Multiple Times | The lead status "New" is shown in multiple locations (SLA banner, lead header, and lead information section), causing redundant information display. | Low | Lead status should be displayed once prominently. | Same status appears multiple times on the page. | Open
BUG-004 | Leads | Lead Details View | SLA Countdown Not Prominent | The SLA timer ("16 min remaining") is displayed at the bottom of the information section and is easy to miss. | Medium | SLA countdown should be highly visible near the top of the page. | SLA information lacks visual emphasis. | Open
BUG-005 | Leads | Lead Details View | Empty Follow-Up and Activity Tabs | Tabs display "Follow Ups (0)" and "Activities (0)" without any empty-state message or action guidance. | Low | Users should see a meaningful empty-state message and CTA. | Empty tabs provide no guidance to users. | Open
BUG-006 | Leads | Lead Details View | Missing Lead Progress Tracker | There is no visual indication of the lead lifecycle (New → Contacted → Qualified → Deal Created). Users cannot quickly identify the lead stage progression. | Medium | A stage/progress tracker should be displayed. | No lead progression indicator is available. | Open
BUG-007 | Leads | Lead Details View | Mark Lost Available for New Lead | The "Mark Lost" action is available immediately for a newly created lead without requiring any interaction or contact attempt. | Medium | System should require at least one activity or confirmation before marking a lead as lost. | Users can mark a new lead as lost directly. | Open
BUG-009 | UI Theme | Dark Mode (All Screens) | Orange Brand Color Changes to Brown in Dark Mode | The primary orange brand color used for buttons, badges, and highlights appears brown when Dark Mode is enabled. This causes inconsistency with the application's design system and weakens the visual prominence of primary actions. | High | The brand orange color should remain visually consistent and accessible across both Light and Dark themes. | In Dark Mode, the orange color is rendered as a brown shade, affecting buttons, status indicators, and highlighted elements. | Open
BUG-010 | Leads | New Leads → Follow Ups | Calendar Icon Not Visible in Dark Mode | The calendar icon used in the Follow Ups section is not visible or has very low visibility when Dark Mode is enabled. Users may not recognize the date selection functionality. | Medium | The calendar icon should be clearly visible and maintain sufficient contrast in both Light and Dark modes. | The calendar icon is hidden, faded, or blends into the background in Dark Mode. | Open
BUG-011 | Leads | Lead Details (Dark Mode) | Orange Theme Color Appears Brown | The orange brand color is rendered as a brown shade in Dark Mode. | High | Brand orange color should remain consistent and clearly visible in both Light and Dark themes. | Orange-colored cards and containers appear brown in Dark Mode. | Open
BUG-012 | Leads | Lead Details (Dark Mode) | Start Qualification Button Has Poor Visibility | The "Start Qualification" action has very low contrast and appears disabled. | High | The button should have sufficient contrast and be clearly identifiable as a clickable action. | The button text blends into the background and looks inactive. | Open
BUG-013 | Leads | Lead Details (Dark Mode) | Low Contrast Between Cards and Background | Lead information cards blend into the page background. | Medium | Cards should be visually distinguishable from the page background. | Cards and background use similar dark shades, reducing section visibility. | Open
BUG-014 | Leads | Lead Details (Dark Mode) | Tab Labels Have Poor Visibility | Overview, Follow Ups, and Activities tabs are difficult to read in Dark Mode. | Medium | Tab labels should maintain adequate contrast and readability. | Tab labels appear faded and less noticeable. | Open
BUG-015 | Leads | Lead Details (Dark Mode) | Inconsistent Dark Theme Color Palette | Different UI elements use inconsistent colors in Dark Mode. | Medium | Theme colors should follow a consistent design system across all components. | Buttons, badges, and cards use mismatched color shades. | Open
BUG-016 | Leads | Lead Details | Duplicate "Add Another Follow-Up" Button | The same action button appears both in the top header and inside the status banner. | Medium | The action should be displayed only once in the most relevant location. | "Add Another Follow-Up" is displayed twice on the same screen. | Open
BUG-017 | Leads | SQL Qualification Popup | Poor Visibility of Disabled "Mark as SQL" Button | The disabled "Mark as SQL" button has very low contrast in Dark Mode and appears almost invisible. | High | Disabled buttons should remain clearly visible while indicating they are inactive. | Button text and icon are difficult to see against the background. | Open
BUG-018 | Leads | SQL Qualification Popup | Low Contrast Placeholder Text | Placeholder values such as "e.g. 500000" and "e.g. Within 1 month" are difficult to read in Dark Mode. | Medium | Placeholder text should maintain accessibility contrast standards. | Placeholder text appears faded and hard to read. | Open
BUG-019 | Leads | SQL Qualification Popup | Repetitive Validation Messages | "Required for SQL" is displayed multiple times after every field, creating visual clutter. | Low | Validation requirements should be displayed once or in a concise format. | The same message is repeated multiple times. | Open
BUG-020 | Leads | SQL Qualification Popup | Inconsistent Mandatory Field Indication | Budget and Timeline fields are marked mandatory (*), but Decision Maker and Genuine Lead checkboxes are also mandatory without a clear mandatory indicator. | Medium | All mandatory fields should have consistent indicators. | Checkboxes appear optional until the warning message is read. | Open
BUG-021 | Leads | SQL Qualification Popup | Close Icon Visibility Issue | The close (X) icon in the top-right corner has poor visibility against the dark header background. | Medium | Close icon should be clearly visible and easy to identify. | Close icon appears faded and difficult to notice. | Open
BUG-022 | Leads | SQL Qualification Popup | Brown Tint Applied to Modal Background | Modal header and footer use a brown shade instead of the application's primary orange theme color. | Medium | Theme colors should remain consistent in Dark Mode. | Brown color is displayed instead of brand orange. | Open
BUG-023 | Leads | SQL Qualification Popup | Warning Banner Has Low Readability | The warning message at the bottom has weak contrast between text and background. | Medium | Warning messages should be easily readable and visually distinct. | Text visibility is reduced in Dark Mode. | Open
BUG-026 | Leads | SQL Qualification Success Popup | Unnecessary Actions Displayed After SQL Qualification | After successfully qualifying a lead as SQL, the popup displays multiple actions: "Convert Lead", "View SQL Leads", and "Add More Activities". These actions may confuse users and create unnecessary decision points. | Medium | After SQL qualification, the popup should display only the relevant action "View SQL Leads" and a close option. | The popup displays additional actions such as "Convert Lead" and "Add More Activities". | Open
BUG-027 | Leads | SQL Lead Details | Duplicate "Convert Lead" Button | The "Convert Lead" action appears both in the top action bar and inside the SQL status banner. | Medium | Convert Lead should be displayed once as the primary action. | Same action is visible in two locations. | Open
BUG-028 | Leads | SQL Lead Details | "Add SQL Activity" Has Low Visibility | The "Add SQL Activity" option has low contrast and does not appear as a primary clickable action. | Medium | Action links should be clearly visible and identifiable. | The action blends into the banner background. | Open
BUG-029 | Leads | SQL Lead Details | "View SQL Leads" Has Low Visibility | The "View SQL Leads" action is difficult to notice because of insufficient contrast in Dark Mode. | Medium | Secondary actions should remain readable in Dark Mode. | Text appears faded. | Open
BUG-030 | Leads | SQL Lead Details | Activity Count Mismatch | Lead is already qualified as SQL, but Activities tab still shows 0 activities. Qualification itself should generate an activity log entry. | High | Qualification activity should be recorded and reflected in the Activities count. | Activities tab displays 0 after SQL qualification. | Open
BUG-031 | Leads | SQL Lead Details | Follow-Up Count Not Updated Based on SQL Actions | After qualification and progression, follow-up/activity history should reflect the lead journey. | Medium | Timeline should show all qualification actions. | Lead progression is not visible in activity history. | Open